## WBS
Work Breakdown Structure | [5 empty] | CocomoMdS
© 2017 by Vertex42.com
Inizio Progetto |  | 2022-12-14 |  |  |  |  | Work Breakdown Structure
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Fase 1
2 | 1.1 | Analisi consegna | Klein, Imran, Garonzi | 2022-12-14 | 2022-12-14
2 | 1.2 | Raccolta Dati | Klein, Imran, Garonzi | 2022-12-14 | 2022-12-14
2 | 1.3 | Compilazione WBS, RACI, OBI | Klein | 2022-12-14 | 2022-12-14
1 | 2 | Fase 2
2 | 2.1 | Scelta del linguaggio da usare (python) | Klein, Imran, Garonzi | 2022-12-17 | 2022-12-17
2 | 2.2 | Creazione file e stesura idea | Imran | 2022-12-17 | 2022-12-17
2 | 2.3 | Ricerca keywords dei linguaggi scelti e creazione dizionari | Imran | 2022-12-17 | 2022-12-17
2 | 2.4 | Inserimento input con relativi controlli | Imran | 2022-12-17 | 2022-12-17
2 | 2.5 | Realizzazione della funzione che conta le keywords con output | Imran | 2022-12-17 | 2022-12-17
2 | 2.6 | Ottimizzazione del codice e test | Imran | 2022-12-17 | 2022-12-17
2 | 2.7 | Gestione file README | Klein | 2022-12-17 | 2022-12-17
1 | 3 | Fase 3
2 | 3.1 | Aggiunta delle percentuali di compatibilità dei linguaggi | Garonzi | 2022-12-18 | 2022-12-18
2 | 3.2 | Creazione file da usare per test | Garonzi | 2022-12-18 | 2022-12-18
2 | 3.3 | Test e eventuale correzione di bug | Garonzi | 2022-12-18 | 2022-12-18
2 | 3.4 | Commentare il codice | Garonzi | 2022-12-18 | 2022-12-18
2 | 3.5 | Gestione file README | Klein | 2022-12-18 | 2022-12-18