## WBS
Work Breakdown Structure | [5 empty] | Cocomo-Mds
© 2017 by Vertex42.com
| Project Start | Ven, Dec 2022/16 |  |  |  |  | Work Breakdown Structure
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Phase 1 |  |  |  |  | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Trovare keywords dei linguaggi | Villardi, Kasun | 2022-12-16 | 2022-12-16
2 | 1.2 | impostare struttura callback.py | Serratore | 2022-12-16 | 2022-12-16
1 | 2 | Phase 2
2 | 2.1 | Richiesta in input del file | Kasun | 2022-12-16 | 2022-12-16
3 | 2.1.1 | leggere file | Kasun | 2022-12-16 | 2022-12-16
3 | 2.1.2 | Trovare estensione file | Kasun | 2022-12-16 | 2022-12-16
4 | 2.1.2.1 | cerca keyword nel file per ogni linguaggio | Serratore | 2022-12-16 | 2022-12-17
5 | 2.1.2.1.1 | prendere linguaggio con più keyword trovate | Serratore | 2022-12-16 | 2022-12-17
1 | 3 | Phase 3
2 | 3.1 | Comparare linguaggio trovato con estensione |  | 2022-12-16 | 2022-12-17
3 | 3.1.1 | Mostrare output | Serratore | 2022-12-16 | 2022-12-17
4 | 3.1.1.1 | formattare script secondo PEP8 | Serratore | 2022-12-16 | 2022-12-17
2 | 3.2 | Realizzare markdown | Villardi | 2022-12-16 | 2022-12-18
◄ Add new rows ABOVE this one.

## Help
HELP
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html |  | © 2017 Vertex42 LLC
About this Template
This template provides a very basic WBS table that you can use for defining a hierarchical work breakdown structure for a project plan or process.
Want more features and automation?
Try the Gantt Chart Template by Vertex42.com
Note: The formula for the WBS numbering was developed by Vertex42.com for the Gantt Chart Template Pro spreadsheet, and is copyrighted. See the terms of use.
Instructions
1) | Choose a Level from the drop-down list in column B. The WBS code is created automatically. When adding rows, you will need to copy the formula in the WBS code column into the newly added rows.
2) | Indent Task Descriptions using the Indent buttons in the Home tab.
3) | Add or hide columns as needed.
4) | A conditional formatting rule automatically highlights level 1 tasks. Go to Home > Conditional Formatting > Manage Rules to remove or edit this rule.
Terms of Use
See the following page for information about how you may use this spreadsheet.
https://www.vertex42.com/licensing/EULA_privateuse.html
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.